## Sheet1
Tasks | Start date | End date | Duration
1- Define project objectives and key deliverables. | 2025-03-20 | 2025-03-23 | 3
2- Brainstorm the initial concept for the visual identity and platform. | 2025-03-24 | 2025-03-27 | 3
3- Draft the design strategy and branding approach. | 2025-03-28 | 2025-04-01 | 4
4- Sketch logo concepts and refine ideas. | 2025-04-03 | 2025-04-06 | 3
5- Digitally design the logo and finalize the primary branding elements. | 2025-04-07 | 2025-04-12 | 5
Review and finalize the brand identity package. | 2025-04-13 | 2025-04-16 | 3
6- Design posters and digital ads | 2025-04-17 | 2025-04-23 | 6
7- Create social media visuals | 2025-04-24 | 2025-04-30 | 6
8- Publish the designs on creative platforms | 2025-05-01 | 2025-05-03 | 2
9- Share on social media & gather feedback | 2025-05-04 | 2025-05-06 | 2
10- Present in an online portfolio/exhibition | 2025-05-07 | 2025-05-08 | 1
| 2025-05-09 | 2025-05-09 | 1